**TNTLab Meeting Minutes**

**Date**: 10/17/2017

**Attendance**: Richard, Bo, Andrew, Elena, Sebastian, Kyle, Martina

1. Richard: Meeting opened

**ANNOUNCEMENTS – none**

**ONGOING BUSINESS**

**ACTION ITEM (ANDREW):** Andrew should submit at least 2 journal submissions (Thesis & Mturk), but ideally 3 this semester (maybe Revelian)

Update: Made progress on thesis submission and sent to Richard for edits. Once that is sent he will work on the Mturk project submission.

1. Elena: Implementing article discussion. Finding articles that are both readable by URAs and relevant to current lab research is difficult.

**DECISION: Hold off on article discussion until we have a few more URAs**

1. Revelian

**ACTION ITEM (MARTINA & KYLE):** Need drop off new flyers every two weeks at help-desk in Webb

**ACTION ITEM (BO):** **Email Richard with most recent batch of participants for payments**

Updated: Done

**ACTION ITEM (ANDREW): Andrew needs to test what Bo sent him (swapping links, change two pages of instruction)**

Updated: Done   
**ACTION ITEM (RICHARD/BO/ANDREW):** schedule a lab get together with Revelian at SIOP this year

**DECISION:** As soon as we hit participant threshold (~500) with Revelian, should submit as JAP article – probably November

**UPDATE:**

**Richard**: 508 completions as of today but about a dozen aren’t real cases, we should begin working on the paper in late October

**ACTION ITEM (RICHARD & BO): find the 4 people with links and send UINs to Bo who will check to see that there’s a reaction time measure**

Richard: We eventually want to use qualtric’s API to integrate with the R script so that we don’t need to keep pulling the data from qualtrics.

1. Elena: Thesis

Discussed new draft and timeline for data collection

**ACTION ITEM (ELENA): Edit thesis draft**

**ACTION ITEM (ELENA): Start drafting IRB materials**

**ACTION ITEM (ELENA): File paperwork with Peggy today**

**DECISION: Next submission for IRB is Nov 6, we will aim for that deadline**

1. Sebastian – FYP

**ACTION ITEM (SEBASTIAN): Create hypothesis and identify measures – due in 2 weeks – specifically, finalize intention measures, study design, use dual lingo logistics, and write up a draft methods section and specific hypotheses**

UPDATE: Drafted and sent to Richard

Discussed measures and paper writing in general – every paragraph should be making a point towards the goal of the paper

**ACTION ITEM (SEBASTIAN): Begin to draft IRB Materials**

**OLD BUSINESS**

1. Interdisciplinary project- one final stage of data collection

**ACTION ITEM (RICHARD): develop final version of data file, final restructuring**

UPDATE- tried to create the final data file but ran into some errors and need to re-run the entire thing

1. Richard: Twitter PNAS submission

Figures need to be in full color, change in-text references for LaTeX formatting, drop text below figure

**ACTION ITEM (ELENA): update figures for PNAS submission**

UPDATE: Done

Next step is finalizing the draft so that it can be converted to LaTeX

**NEW BUSINESS**

1. Richard: Discussed new graduate student funding policy
2. Richard: Discussed IRB process: there are two paths 1) committee for college of science (fast- survey based research study is anonymous or confidential without sensitive information), and 2) full IRB expedited and full review- one person reads it (expedited) or full IRB (entire IRB reads it and you are encouraged and expected to attend the meeting.
3. Richard: Going to Nebraska on Thurs/Friday for a web scraping presentation
4. Richard: Psi SJT project- gradually working through the lawyers
5. Bo: Briefly discussed dissertation and theory building