**TNTLab Meeting Minutes**

**Date**: 11/21/2017

**Attendance**: Richard, Bo, Andrew, Elena, Sebastian, Martina, Kyle

1. Richard: Meeting opened

**ANNOUNCEMENTS – none**

**ONGOING BUSINESS**

**ACTION ITEM (ANDREW):** Andrew should submit at least 2 journal submissions (Thesis & Mturk), but ideally 3 this semester (maybe Revelian)

**DECISION:** We should have a draft of the MTurk Paper by finals week

1. Revelian

**ACTION ITEM (RICHARD/BO/ANDREW):** schedule a lab get together with Revelian at SIOP this year

**DECISION:** As soon as we hit participant threshold (~500) with Revelian, should submit as JAP article

Update: We’ve hit 730 participants

**DECISION:** Wednesday the 17th should be the last day of recruitment. After recruitment is finished, paperwork should be finalized and top participants should be payed. Paperwork should be filed on the 18th

Richard: For next round of fliers, we should say “Last chance, winners payed on 18th”

**ACTION ITEM (RICHARD, BO, ANDREW):** Create an analytic plan for paper write-up

**ACTION ITEM (BO, MARTINA, KYLE):** Create a google doc sheet with cites for each cog test- one or two cites per each specific ability (6), and for each of the 18 tests we need source citation and use in context citation

Update: URAs are currently working on the lit review

**DECISION: Lit review should be complete within the next two weeks**

1. Elena: Thesis

**ACTION ITEM(ELENA):** Have thesis materials prepped for Nov 28th lab meeting

* We’ll talk about it and then lab members will give feedback via email
* Goal is to have the study running on the day SONA opens

Should have thesis proposal edits done towards the end of January

1. Sebastian – FYP

**ACTION ITEM(SEBASTIAN):** Have FYP materials prepped for Nov 28th lab meeting

**ACTION ITEM (SEBASTIAN):** Make progress on draft using Richard’s feedback and consider pre-registration

**OLD BUSINESS**

1. Richard: Twitter PNAS submission

**ACTION ITEM (RICHARD):** Finalize draft so that it can be converted to LaTeX

**ACTION ITEM (ELENA):** Make final changes to tables so that we can send draft to Ross

1. Mobile Diversity project

**ACTION ITEM (RICHARD & ELENA):** Respond to select international’s email

**NEW BUSINESS**

1. Richard: Visiting Scholar from Iran (Mohadeseh)

* Has proposed her dissertation and is looking to collect data and work on other projects while she is here
* She will likely arrive either in December or January and stay through the spring semester

Discussed some ideas for activities to do while she’s here

* Have dinner at a grad student’s house
* Escape room
* Williamsburg/Busch gardens
* Travel to DC for the Tech conference in Lab van

Discussed things we need to do to prepare for her arrival

* Martina offered to help with cultural transition and housing
* We need to prepare the office/her workspace

**ACTION ITEM (ALL LAB MEMBERS):** Decide where her desk will go (current grad student office, psych dept office, lab, etc)

1. Richard: Discussed SIOP Machine learning competition

* We’ll be tasked with predicting turnover

**ACTION ITEM (ELENA & RICHARD):** Set up github for this project, check out the free private repository options on github

1. Richard: Discussed Big Data Computing Seminar, people interested in attending should register asap
2. Richard: Discussed Star Wars lab activity
   * A Matinee would be ideal