**TNTLab Meeting Minutes**

**Date**: 11/28/2017

**Attendance**: Richard, Bo, Andrew, Elena, Sebastian, Martina, Kyle

1. Richard: Meeting opened

**ANNOUNCEMENTS – Final Meeting of Semester**

**ONGOING BUSINESS**

**ACTION ITEM (ANDREW):** Andrew should submit at least 2 journal submissions (Thesis & Mturk), but ideally 3 this semester (maybe Revelian)

**DECISION:** We should have a draft of the MTurk Paper by finals week

1. Revelian

**ACTION ITEM (RICHARD/BO/ANDREW):** schedule a lab get together with Revelian at SIOP this year

**DECISION:** As soon as we hit participant threshold (~500) with Revelian, should submit as JAP article

Update: We’ve hit 730 participants

**DECISION:** Wednesday the 17th should be the last day of recruitment. After recruitment is finished, paperwork should be finalized and top participants should be payed. Paperwork should be filed on the 18th

**ACTION ITEM (BO):** send out email with final deadline to everyone on the list that hasn’t done it yet

**ACTION ITEM (RICHARD, BO, ANDREW):** Create an analytic plan for paper write-up

**ACTION ITEM (BO, MARTINA, KYLE):** Create a google doc sheet with cites for each cog test- one or two cites per each specific ability (6), and for each of the 18 tests we need source citation and use in context citation

Update: URAs are currently working on the lit review

**DECISION: Lit review should be complete within the next two weeks**

**ACTION ITEM (RICHARD):** Contact Revelian

1. Elena: Thesis

**ACTION ITEM(ELENA):** Finalize procedure for thesis and send out to lab for testing

Should have thesis proposal edits done towards the end of January

1. Sebastian – FYP

**ACTION ITEM(SEBASTIAN):** Finalize procedure and send out to lab for testing

**OLD BUSINESS**

1. Richard: Twitter PNAS submission

**ACTION ITEM (ELENA):** Write a brief description of the datasetsfor PNAS submission

1. Mobile Diversity project

**ACTION ITEM (RICHARD & ELENA):** Respond to select international’s email

1. Richard: Visiting Scholar from Iran (Mohadeseh)

**ACTION ITEM (ALL LAB MEMBERS):** Decide where her desk will go (current grad student office, psych dept office, lab, etc)

1. Richard: Discussed SIOP Machine learning competition

* We’ll be tasked with predicting turnover

**ACTION ITEM (ELENA & RICHARD):** Set up github for this project, check out the free private repository options on github

**NEW BUSINESS**

1. Richard: Discussed Star Wars movie lab event
   * Tara Behrend will be in town
   * December 15th is the best date, ideally around 5 pm
   * Andrew will coordinate logistics

**ACTION ITEM (ANDREW):** Coordinate Star Wars Movie Lab Event

1. Elena: Presented procedure for Master’s thesis
2. Sebastian: Presented procedure for FYP